## Introduction
ML Project Governance Framework | ML Project Governance Framework is a framework that can be followed by any new Data Science business or team. It will help in formulating strategies around how to use Data Science as a business, how to architect Data Science based solutions and team formation strategy, typical Data Science project lifecycle components, commonly available Deep Learning toolsets and frameworks and best practices used by Data Scientists.
Reference | https://github.com/indranildchandra/ml-project-governance-framework

## Data Science as a Business
Reference: https://www.business-science.io/bspf.html

## Data Science Solution Plan
Step 1: | Business Understanding
Keypoints:
1 | Identify the problem statement and use KPIs to define it.
2 | Identify your customers and users.
3 | Do ROI calculation. Clearly define and quantify the business benefits.
4 | Do a feasibility analysis for architecting a rule based solution.
5 | Inspect the quality of available data at a high level and whether it can be used to build a ML/DL based solution.
6 | Evaluate the risk of exposing production data to the team. Use methods like Vignere Cipher to mask PII data. Consult and get approvals from Information Security champion in your team.
7 | Remember to involve all stakeholders in the above discussions (Business Owner, BA, Data Scientist, Data Engineers, DevOps, etc.). Do not exercise transactional operating model while building a Data Science solution.
Primary Owner: | Business Analyst
# of people: | 1 BA and Business Owner (someone who interacts directly with the users as well as customers).
Step 2: | Data Acquisition and Understanding
Keypoints:
1 | Define your Data Source: - On-premises vs Cloud - Database vs Files
2 | Define your Data Pipeline: - Streaming vs Batches - Low vs High Frequency Data
3 | Environment Setup: - On-premises vs Cloud - Database vs Data Lake - Small vs Medium vs Big Data
4 | Wrangling, Exploration and Cleaning: - Structured vs Unstructured Data - Data Validation and Cleanup - Data Visualization
Primary Owner: | Data Engineer
# of people: | 1 Data Engineer with prior experience using technologies like Apache Spark, Apache Storm, Apache Kafka, HDFS, NoSQL, etc. Optional to have junior software engineer as a backup.
Step 3: | Modeling
Keypoints:
1 | Feature Engineering: - Work with BA to define features. - Evaluate features (in terms of Model evaluation metrics as well as statistical measures). - Check for corelated features and combine them statistically. - Document every feature for future reference, even if it is discarded. Discarded feature generation principles can be reused for other projects.
2 | Model Training: - Decide the algorithm to be used. If needed proceed with an Ensemble based approach. - Do Hyper-parameter optimization and parameter tuning. - Retrain the models. Remember to use Transfer Learning judiciously and not overfit the models by retraining repeatedly. - Manage Model versions.
3 | Model Evaluation: - Use K-fold cross validation to evaluate model performance. - Report model results using visualization and reporting tools. - Use A/B testing in UAT and verify if the users notice any abruptions or disruptions.
Primary Owner: | Data Scientist
# of people: | 1 Data Scientist with prior experience and knowledge of statistics, linear algebra, calculus, probability and familiarity with State of the Art techniques. 1 junior software engineer or a budding data scientist can be included as a backup and/or for Data Scientist skill building.
Step 4: | Deployment
Keypoints:
1 | Responsible for model storing and exposing them as web services.
2 | Responsible for setting up and maintaining the infrastructure.
3 | Responsible for model scoring, performance monitoring and giving feedback to the rest of the team on any reported issues or abnormalities.
Primary Owner: | Software Engineer and DevOps Engineer
# of people: | 1 Software Engineer with prior experience in building web based solutions (building REST APIs, authentication, etc.). 1 DevOps Engineer with hands-on knowledge of all DevOps related components including containerization (Docker), container orchestration (Kubernetes), continous integration (Jenkins), continous deployment, Infrastructure-as-a-Service and cloud platforms (AWS/GCP/Azure Cloud).

## ML Project Lifecycle Phases
Supervised Learning Project Lifecycle
Reference: https://www.luminovo.ai/

## DL Toolsets and Frameworks
Reference: https://www.luminovo.ai/

## Data Science - Best Practices
List of Best Practices practiced by Data Scientists
Sr. No. | Summary | Solution
1 | Share Data Referenced in Code | Use d6tpipe to share data files with your code or upload to S3/web/google drive etc or save to a database so the recipient can retrieve files (but don't add them to git).
2 | Always refer to relative paths in code | Use relative paths, global path config variables or d6tpipe to make your data easily accessible.
3 | Organize your directory structure | Organize your directory into categories, like data, reports, code etc. Use tools mentioned in #1 to store and share data.
4 | Do not commit data, unless you use the right tool to do so | Use tools mentioned in #1 to store and share data. If you really want to version control data, see d6tpipe, DVC and Git Large File Storage.
5 | Write DAGs instead of functions | Instead of linearly chaining functions, data science code is better written as a set of tasks with dependencies between them. Use d6tflow or airflow.
6 | Do not write for loops | Numpy, scipy and pandas have vectorized functions for most things that you think might require for loops.
7 | Write unit tests | Use assert statements to check for data quality. pandas has equality tests, d6tstack has checks for data ingestion and d6tjoin for data joins.
8 | Document your code | Take the extra time, even if it's after you've delivered the analysis, to document what you did. You will thank yourself and other will do so even more!
9 | Do not store your data as csv or pickle file | Use parquet or other binary data formats with data schemas, ideally ones that compress data. d6tflow automatically saves data output of tasks as parquet so you don't have to deal with it.
10 | Do not use Jupyter Notebooks for writing production grade code | Use pycharm and/or spyder.